## Slide 1
IARPC Sea Ice Collaboration Team:
Organizing, Tracking, Modifying & Creating Milestones
There is a large number IARPC Sea Ice milestones and at first glance they appear somewhat confusing. In attempt to make our efforts look more coherent and organized, I propose that we assign our milestones to one of three categories (let’s call them thrusts): “Observing”, “Understanding” & “Predicting” (see slide 3). Each thrust has a list of topics that I think belong there and which the Sea Ice team would consider for future research and thus milestones.
I then summarize the status of the current milestones according to each thrust. Having eliminated the completed milestones, I then take the remaining milestones in each thrust and do four things: (1) rewrite some milestones to make the meaning clearer without changing the original intent; (2) rationalize some milestones by consolidating them under a single heading; (3) change some completion dates to allow more time; and (4) leave some milestones unchanged.
We don’t want to be slaves to milestones, but we do have an obligation to report regularly on milestone progress and completion, and to develop new milestones. I hope this straw man organization by three thrusts, and modification of current milestones, will help us do better at both.

## Slide 2
Our milestones are found in two activities in the IARPC 5-year Research Plan (officially the Arctic Research Plan). Below, in black, is the original activity title, and, in blue, a proposed modification of each to better describe what we’re doing. Between them, the two activities cover Observing, Understanding, and Predicting, the proposed categories and organizational structure in the next slide (3).
IARPC Sea Ice Activities
Original: Develop a framework of observations and modelling to support forecasting of sea-ice extent on seasonal to annual timescales for operational and research needs.
Modified: Develop a program of sustained observations and modelling to support sea ice forecasting on seasonal to annual timescales for operational and research needs.
Original: Identify and study sites in the Beaufort and Chukchi seas and contiguous Arctic Ocean where climate feedbacks are active.
Modified: Understand climate feedback processes in the Beaufort and Chukchi seas and the contiguous Arctic Ocean.
IARPC Sea Ice Activities

## Slide 3
IARPC Sea Ice Collaboration Team:
Three Thrusts for Organizing Milestones
Observing
Sustained Observations
Observing System Design
Sensors & Sensor Systems
Platforms
Data Relay and Transfer
Products and Services
Understanding
Field Investigations
Process Models
Analysis and Synthesis
Products and Services
(Publications)
Predicting
Fully Coupled Models
Data Assimilation
Simulate or Parameterize?
Performance Evaluation
Products and Services

## Slide 4
Current Milestones: Observing
3.1.1.d --- Launch Ice, Cloud, and land Elevation Satellite (ICESat) 2 satellite altimetry mission to continue the record of sea-ice thickness measurements and land ice elevation change. 2016. In progress
3.1.1.d --- Launch Gravity Recovery and Climate Experiment (GRACE) Follow-On satellite mission to continue the record of changes in Arctic Ocean circulation and land ice mass loss. 2017. In progress
3.1.1.f --- Develop algorithms for the Advanced Microwave Scanning Radiometer 2 (AMSR2), recently launched on Japan’s GCOM-W, to continue and enhance passive microwave record of sea-ice extent. 2014. Status?
3.1.2.j --- Continue operation IceBridge acquisition of sea-ice surface elevation and supporting data, and expand Arctic sea-ice observations to constrain melting processes. 2017. In progress
3.1.2.f --- Develop and test large-class, heavy payload unpiloted aerial systems (UAS) for sea-ice characterization. 2014.
Cancelled or Postponed?

## Slide 5
Current Milestones: Understanding – Part 1
3.1.2.c --- Work through the Oil Spill Recovery Institute in conjunction with State of Alaska and response organizations to apply research results to oil spill response planning. 2013. No action taken
3.1.1.g --- Improve knowledge of sea-ice melting through various activities such as ONR’s marginal ice zone program and NASA’s Operation IceBridge mission. 2017. In progress
3.1.2.d --- Investigate the marginal ice zone.
ONR, Emerging Dynamics of the Marginal Ice Zone DRI. 2016.
In progress
3.1.2.e --- NASA/NOAA, Marginal Ice Zone Observations and Processes Experiment – MIZOPEX. 2013.
Completed?
3.1.2.g --- Investigate sea-state and boundary layer physics in the emerging Arctic Ocean. 2017. In progress

## Slide 6
Current Milestones: Understanding – Part 2
3.1.2.i --- Investigate characterization of the circulation on the continental shelf areas of the Northeast Chukchi and Western Beaufort seas. 2012. Status?
3.1.2.n --- Identify optimal sites for short-term process studies underpinned by long-term observations. 2014. What does this mean?
3.1.2.k --- Initiate interagency evaluation of trends and significance of methane flux to the atmosphere in Arctic regions. 2015. Status?
3.1.2.l --- Initiate a dialogue with Roshydromet and Russian Academy of Science on a potential investigation of the current rate of methane release from the shallow shelves off northern Siberia. 2013. Status?
3.1.2.m --- Initiate a dialogue with Canadian agencies on collaborative methane research along the Beaufort Sea coast. 2013. Status?

## Slide 7
Modified Milestones: Understanding
Investigate marginal ice zone processes in summer in the Arctic Ocean. 2017.
Consolidation of 3.1.1.g, 3.1.2.d & 3.1.2.e
Investigate sea-state and boundary layer physics in the emerging Arctic Ocean. 2017. 3.1.2.g
Investigate methane release from the continental shelf, and evaluate of trends and significance of methane flux to the atmosphere. 2017.
Consolidation of 3.1.2.k, 3.1.2.l & 3.1.2.m
Apply sea ice research and forecasting results to oil spill response planning. 2017. 3.1.2.c Re-written
Identify optimal sites for short-term process studies underpinned by long-term observations. 2014. 3.1.2.n Re-word for something useful?
Investigate characterization of the circulation on the continental shelf areas of the Northeast Chukchi and Western Beaufort seas. 2012. 3.1.2.i Status?

## Slide 8
Current Milestones: Predicting
3.1.1a --- Convene interagency expert group on sea-ice forecasting to develop multi-year implementation plan, coordinate ongoing observation and modeling, and determine needed improvements to reduce uncertainty in forecasts. 2013. Completed or in progress?
3.1.1.b --- Engage with stakeholders and users to determine needs for sea-ice forecasts and products through venues such as the Alaska Marine Science Symposium and Alaska Forum on the Environment. 2013. Completed?
3.1.1.c --- Continue the Sea Ice Outlook and Sea Ice for Walrus Outlook to evaluate diverse sea-ice forecasting approaches and fill a valuable user need. 2013. Completed.
3.1.2.a --- Report of a workshop on sea-ice forecasting. 2012. Completed.
3.1.2.b --- Report of a workshop on the future of Arctic sea-ice research and forecasting, National Academy Polar Research Board. 2013. Completed
3.1.2.h --- Initiate interagency activity to improve application of remote sensing and buoy/mooring data to sea-ice forecasting. 2012. Status? Postponed or Cancelled?
3.1.2.o ---- Undertake a sea ice model intercomparison project in order to improve sea ice prediction at a variety of time and space scales. 2017. In progress

## Slide 9
Modified Milestones: Predicting
3.1.1a --- Convene interagency expert group on sea-ice forecasting to develop multi-year implementation plan, coordinate ongoing observation and modeling, and determine needed improvements to reduce uncertainty in forecasts. 2013. In progress?
3.1.2.h --- Improve application of remote sensing and buoy/mooring data to sea-ice forecasting
i.e., data assimilation. 2017. Re-written and new completion date.
3.1.2.o --- Undertake a sea ice model intercomparison project in order to improve sea ice prediction at a variety of time and space scales. 2017. In progress
This cupboard looks a little bare.
An opportunity for new milestones?
We should look at the IARPC Modeling Collaboration Team milestones for further synergies à la the Sea Ice Prediction Network.